## Time
Deliverables | Est | Current | Left to do | Notes | Week 1 | Week 2
Physics Engine | 2 | 3 | -1 | Mostly done | 3.5 hours to planning/overhead | Completed gyro taskk in 0.5x estimated time. 1.5 hours to overhead, 0.75 hours to gyro task
Gyro Angle | 1.5 | 2 | -0.5 | Done
Screen Display | 8 | 4 | 4 | Likely meat of the project, reading from multiple tasks
Obstacle Task | 4 | 2 | 2 | Pretty much done | Week 3
Quantum Task | 2.5 | 0 | 2.5 | Not started | 1 hour to overhead, 2 hours to physics engine, another 0.75 hour to gyro angle cleaning it up, 2hours to screen display.
LED Task | 1.5 | 0 | 1.5 | Not started
Planning/Overhead | 10 | 7 | 3 |  | Week 4
3 hours to obstacle, got the maze generated (not random)
0.5 hour to gyro
TOTAL EST. | 29.5 |  |  |  | 1 hour to physics
TOTAL CURR | 18 |  |  |  | 2 hour to screen display
TOTAL LEFT | 11.5 |  |  |  | 1 hour to overhead (research on maze theory and thinking about collisions)

## Risk Register
Item | P | I | Risk (P*I) | Recognized | Mitigated/ Resolved | ROAM | How
Generating randomized obstacles | 70 | 1 | 70 | 2024-03-20 |  | A | Not true random is accepted for MVP
Mutexes causing tasks to be slow because I am making a lot of things globals | 20 | 20 | 400 | 2024-03-20 | M | M | Can make remove a mutex from ball properties by using a semaphore from phys task to lcd task whenever position should be updated
Senioritis and planning for post grad | 70 | 40 | 2800 | 2024-03-20 |  | A | It is what it is
Computation heavy tasks don't get as much CPU time | 20 | 70 | 1400 | 2024-04-05 |  | O | I think I will change task priority levels but I can't test for awhile
Can't get system view to work on mac | 100 | 8 | 800 | 2024-04-12 |  | A | Will have to run on a windows device, could be my desktop at home
Latency for checking collisions | 40 | 70 | 2800 | 2024-04-19 |  | O | Have some thoughts about how to speed it up (BST based on position)
Circular holes being too difficult to check against | 70 | 5 | 350 | 2024-04-19 | Resolved | R | Square holes
0
0

## Tests
Unit Tests | Tested? (Y/N) | P/F | Func Tests | Tested? (Y/N) | P/F
Physics task updates ball struct acceleration based on angle received. Will test by hard coding it in the physics task and running the computational code segment multiple times serially. | Y | P | Quantum button press decreases green LED luminosity | N
Will hard code the button state var to be pressed, then run the LED task and watch the energy variable decrease. | N |  | Once "energy" is depleted, the green LED increases back to full brightness | N
|  |  | Changing angle of board moves ball "downhill" in that direction | Y | P
|  |  | Board layout is different every time | N
|  |  | Ball falls in hole and resets | N
|  |  | Ball stops at wall | N
|  |  | Board has layout path for ball to take | N
|  |  | When quantum button pressed, ball moves through walls and over holes | N

## Fib vals
Valid Modified Fibonacci values
1
2
3
5
8
13
20
40
70
100