## Time
Deliverables | Est | Current | Left to do | Notes | Week 1 | Week 2
Physics Engine | 2 | 0 | 2 |  | 3.5 hours to planning/overhead | Completed gyro taskk in 0.5x estimated time. 1.5 hours to overhead, 0.75 hours to gyro task
Gyro Angle | 1.5 | 0.75 | 0.75
Screen Display | 8 | 0 | 8 | Likely meat of the project, reading from multiple tasks
Obstacle Task | 4 | 0 | 4
Quantum Task | 2.5 | 0 | 2.5
LED Task | 1.5 | 0 | 1.5
Planning/Overhead | 10 | 5 | 5
TOTAL EST. | 29.5
TOTAL CURR | 5.75
TOTAL LEFT | 23.75

## Risk Register
Item | P | I | Risk (P*I) | Recognized | Mitigated/ Resolved | ROAM | How
Generating randomized obstacles | 13 | 70 | 910 | 2024-03-20 |  | O | Nothing to do about it now
Mutexes causing tasks to be slow because I am making a lot of things globals | 20 | 40 | 800 | 2024-03-20 |  | O | Nothing to do about it now
Senioritis and planning for post grad | 70 | 40 | 2800 | 2024-03-20 |  | A | It is what it is
Computation heavy tasks don't get as much CPU time | 20 | 70 | 1400 | 2024-04-05 |  | O | I think I will change task priority levels but I can't test for awhile
0
0
0
0
0

## Tests
Unit Tests | Tested? (Y/N) | P/F | Func Tests | Tested? (Y/N) | P/F
Physics task updates ball struct acceleration based on angle received. Will test by hard coding it in the physics task and running the computational code segment multiple times serially. | N |  | Quantum button press decreases green LED luminosity | N
Will hard code the button state var to be pressed, then run the LED task and watch the energy variable decrease. | N |  | Once "energy" is depleted, the green LED increases back to full brightness | N
|  |  | Changing angle of board moves ball "downhill" in that direction | N
|  |  | Board layout is different every time | N
|  |  | Ball falls in hole and resets | N
|  |  | Ball stops at wall | N
|  |  | Board has layout path for ball to take | N
|  |  | When quantum button pressed, ball moves through walls and over holes | N

## Fib vals
Valid Modified Fibonacci values
1
2
3
5
8
13
20
40
70
100