## Time
Deliverables | Est | Current | Left to do | Notes | Week 1
Physics Engine | 2 | 0 | 2 |  | 3.5 hours to planning/overhead
Gyro Angle | 1.5 | 0 | 1.5
Screen Display | 8 | 0 | 8 | Likely meat of the project, reading from multiple tasks
Obstacle Task | 4 | 0 | 4
Quantum Task | 2.5 | 0 | 2.5
LED Task | 1.5 | 0 | 1.5
Planning/Overhead | 10 | 3 | 7
TOTAL EST. | 29.5
TOTAL CURR | 3
TOTAL LEFT | 26.5

## Risk Register
Item | P | I | Risk (P*I) | Recognized | Mitigated/ Resolved | ROAM | How
Generating randomized obstacles | 13 | 70 | 910 | 2024-03-20 |  | O | Nothing to do about it now
Mutexes causing tasks to be slow because I am making a lot of things globals | 20 | 40 | 800 | 2024-03-20 |  | O | Nothing to do about it now
Senioritis and planning for post grad | 40 | 40 | 1600 | 2024-03-20 |  | A | It is what it is
0
0
0
0
0
0

## Unit Tests
Unit Tests | Tested? (Y/N) | P/F
Angle vals is read into physics task when board angle is changed | N
LED receives messages of energy bar state from simmed button presses | N

## Fib vals
Valid Modified Fibonacci values
1
2
3
5
8
13
20
40
70
100